## Slide 1: SAS Decommissioning Programme
Status review | Q4 2026
Self-directed project. Synthetic data; no real organisational data is used.
Notes: Simulation of a legacy analytics decommissioning programme, built on a synthetic 60-asset inventory.

## Slide 2: Where the programme stands
60
Assets in scope
40%
Complete
36
Assets remaining
895
Person-days remaining
Chart: Assets by migration status
| In migration | Migrated | Decommissioned | Not started | Discovery | Testing
Assets | 16 | 13 | 11 | 8 | 7 | 5
Notes: 24 of 60 assets are already finished. Notably 11 were decommissioned rather than migrated, so retiring assets is established practice on this programme.

## Slide 3: Cost to complete, by department
Chart: 
| Marketing Analytics | Finance | Actuarial | Claims | Risk & Compliance | Underwriting
Cost to complete | 270200 | 141200 | 132900 | 111300 | 108250 | 76900
EUR 840,750
total cost to complete
Marketing Analytics holds 32% of the remaining budget despite being the lowest-criticality department in the estate.
Underwriting and Risk & Compliance, where the business-critical work sits, hold the smallest shares.
Notes: The question for the steering committee is not what the costs are, but why a third of the budget sits with the lowest-stakes department.

## Slide 4: Top three risks
11 assets unowned
Eleven Critical or High criticality assets have no assigned owner.
Nobody can confirm what they do, and nobody will sign off the migrated version.
Owner: Discovery workstream
Budget misallocation
Marketing Analytics holds EUR 270,200 of the EUR 840,750 remaining, at the lowest business criticality.
39% of that spend is on assets unused for two years.
Owner: Product Owner
Compliance scope
19 unmigrated assets hold personal data; 12 fall within EU AI Act scope.
Each needs review before migration. Classification requires legal input.
Owner: Compliance workstream
Notes: The unowned assets are the most urgent: they block validation of every migration they touch.

## Slide 5: Decision needed
EUR 322,700
is budgeted to migrate 15 assets that have not been run in over two years.
That is 38% of the entire remaining migration budget.
Eleven assets have already been decommissioned rather than migrated on this programme, so the precedent is established.
Recommendation: pause migration work on all fifteen pending usage confirmation with the owning departments.
Next milestone
Decommission candidate sign-off
Target: Q4 2026
Written confirmation from each owning department that the 15 assets are genuinely dormant
Blocked by: owner assignment for 11 Critical/High assets
Notes: The ask is a pause and a review, not a cancellation. Confirming usage with departments costs days; migrating a dormant asset costs tens of thousands.